## Sheet1
CLIENT | SR. NO. | BRM | Case# | Scope Estimated Hours | Scope Actual Hours | Scope Client Contact & CC Details | Contact 2 | Current Situation | Proposed Solution | Deliverables | Acceptance | Client Responsibility | Issues and Constraints | Price Estimate | Final Resolution
AET |  | Angela C. | [5 empty] | HealthEdge Systems (AET) uses MarketProminence (MP) to manage their Medicare members. To continue compliance into the new year ('2021'), there are multiple data points outlined in the Proposed Solution section of this scope that need to be updated to allow MP to continue processing member transactions properly. | See attached pdf—'MarketProminence Year-end 2021'. | See attached pdf—'MarketProminence Year-end 2021'. | Please verify that all deliverables in the attached file are implemented in test and after internal testing is completed, promoted to production. | The client is responsible for the items listed under client responsibilities in the attached document. Send email to BRM when items are successfully implemented to production. | Any variances determined after loading the January 1st 2021 MMR file will be investigated once the client initiates a new request Angela Clock. | MHK/MarketProminence estimates ___ hours to complete this project. ___ hours will be deducted from the prepaid amount. Any hours over the monthly hours will first be deducted from the current years remaining rollover hours. Hours in excess of the monthly and carryover will be billed at the contracted postpaid rate. | Please email a signed copy of this scope to aclock@mhk.com. Any changes made to this scope will require a new revision and appropriate approvals.
AVM |  | Deb H. | [5 empty] | AvMed (AVM) uses MarketProminence (MP) to manage their Medicare members. To continue compliance into the new year ('2021'), there are multiple data points outlined in the Proposed Solution section of this scope that need to be updated to allow MP to continue processing member transactions properly. | See attached pdf—'MarketProminence Year-end 2021'. | See attached pdf—'MarketProminence Year-end 2021'. | Please verify that all deliverables in the attached file are implemented in test and after internal testing is completed, promoted to production. | The client is responsible for the items listed under client responsibilities in the attached document. Send email to BRM when items are successfully implemented to production. | Any variances determined after loading the January 1st 2021 MMR file will be investigated once the client initiates a new request Deborah Hannon. | MHK/MarketProminence estimates ___ hours to complete this project. ___ hours will be deducted from the prepaid amount. Any hours over the monthly hours will first be deducted from the current years remaining rollover hours. Hours in excess of the monthly and carryover will be billed at the contracted postpaid rate. | Please email a signed copy of this scope to dhannon@mhk.com. Any changes made to this scope will require a new revision and appropriate approvals.
BCA |  | Adam K. | 35254 (scopus not completed) | 35 |  | Beth Stern |  | Blue Cross Blue Shield of Arizona (BCA) uses MarketProminence (MP) to manage their Medicare members. To continue compliance into the new year ('2021'), there are multiple data points outlined in the Proposed Solution section of this scope that need to be updated to allow MP to continue processing member transactions properly. | See attached pdf—'MarketProminence Year-end 2021'. | See attached pdf—'MarketProminence Year-end 2021'. | Please verify that all deliverables in the attached file are implemented in test and after internal testing is completed, promoted to production. | The client is responsible for the items listed under client responsibilities in the attached document. Send email to BRM when items are successfully implemented to production. | Any variances determined after loading the January 1st 2021 MMR file will be investigated once the client initiates a new request Adam Kamen. | MHK/MarketProminence estimates 35 hours to complete this project. 35 hours will be deducted from the prepaid amount. Any hours over the monthly hours will first be deducted from the current years remaining rollover hours. Hours in excess of the monthly and carryover will be billed at the contracted postpaid rate. | Please email a signed copy of this scope to akamen@mhk.com. Any changes made to this scope will require a new revision and appropriate approvals.
BCN |  | Adam K. | 35244 (scopus not completed_ | 25 |  | Donna Siegmund |  | Blue Care Network of Michigan (BCN) uses MarketProminence (MP) to manage their Medicare members. To continue compliance into the new year ('2021'), there are multiple data points outlined in the Proposed Solution section of this scope that need to be updated to allow MP to continue processing member transactions properly. | See attached pdf—'MarketProminence Year-end 2021'. | See attached pdf—'MarketProminence Year-end 2021'. | Please verify that all deliverables in the attached file are implemented in test and after internal testing is completed, promoted to production. | The client is responsible for the items listed under client responsibilities in the attached document. Send email to BRM when items are successfully implemented to production. | Any variances determined after loading the January 1st 2021 MMR file will be investigated once the client initiates a new request Adam Kamen. | MHK/MarketProminence estimates 25 hours to complete this project. 25 hours will be deducted from the prepaid amount. Any hours over the monthly hours will first be deducted from the current years remaining rollover hours. Hours in excess of the monthly and carryover will be billed at the contracted postpaid rate. | Please email a signed copy of this scope to akamen@mhk.com. Any changes made to this scope will require a new revision and appropriate approvals.
BPA | [7 empty] | ????????????????????? (BPA) uses MarketProminence (MP) to manage their Medicare members. To continue compliance into the new year ('2021'), there are multiple data points outlined in the Proposed Solution section of this scope that need to be updated to allow MP to continue processing member transactions properly. | See attached pdf—'MarketProminence Year-end 2021'. | See attached pdf—'MarketProminence Year-end 2021'. | Please verify that all deliverables in the attached file are implemented in test and after internal testing is completed, promoted to production. | The client is responsible for the items listed under client responsibilities in the attached document. Send email to BRM when items are successfully implemented to production. | Any variances determined after loading the January 1st 2021 MMR file will be investigated once the client initiates a new request ______________________. | MHK/MarketProminence estimates ___ hours to complete this project. ___ hours will be deducted from the prepaid amount. Any hours over the monthly hours will first be deducted from the current years remaining rollover hours. Hours in excess of the monthly and carryover will be billed at the contracted postpaid rate. | Please email a signed copy of this scope to ______________________. Any changes made to this scope will require a new revision and appropriate approvals.
CCA |  | Deborah H. | 35256 | 30 |  | Nicole Gordon |  | Commonwealth Care Alliance (CCA) uses MarketProminence (MP) to manage their Medicare members. To continue compliance into the new year ('2021'), there are multiple data points outlined in the Proposed Solution section of this scope that need to be updated to allow MP to continue processing member transactions properly. | See attached pdf—'MarketProminence Year-end 2021'. | See attached pdf—'MarketProminence Year-end 2021'. | Please verify that all deliverables in the attached file are implemented in test and after internal testing is completed, promoted to production. | The client is responsible for the items listed under client responsibilities in the attached document. Send email to BRM when items are successfully implemented to production. | Any variances determined after loading the January 1st 2021 MMR file will be investigated once the client initiates a new request Deborah Hannon. | MHK/MarketProminence estimates 30 hours to complete this project. 30 hours will be deducted from the prepaid amount. Any hours over the monthly hours will first be deducted from the current years remaining rollover hours. Hours in excess of the monthly and carryover will be billed at the contracted postpaid rate. | Please email a signed copy of this scope to dhannon@mhk.com. Any changes made to this scope will require a new revision and appropriate approvals.
CHP |  | Angela C. | [5 empty] | ?????????? (CHP) uses MarketProminence (MP) to manage their Medicare members. To continue compliance into the new year ('2021'), there are multiple data points outlined in the Proposed Solution section of this scope that need to be updated to allow MP to continue processing member transactions properly. | See attached pdf—'MarketProminence Year-end 2021'. | See attached pdf—'MarketProminence Year-end 2021'. | Please verify that all deliverables in the attached file are implemented in test and after internal testing is completed, promoted to production. | The client is responsible for the items listed under client responsibilities in the attached document. Send email to BRM when items are successfully implemented to production. | Any variances determined after loading the January 1st 2021 MMR file will be investigated once the client initiates a new request Angela Clock. | MHK/MarketProminence estimates ___ hours to complete this project. ___ hours will be deducted from the prepaid amount. Any hours over the monthly hours will first be deducted from the current years remaining rollover hours. Hours in excess of the monthly and carryover will be billed at the contracted postpaid rate. | Please email a signed copy of this scope to aclock@mhk.com. Any changes made to this scope will require a new revision and appropriate approvals.
DST |  | Deborah H. | 35258 | 25 |  | Bindu Kuriakose |  | DST Health Solutions, Inc. (DST) uses MarketProminence (MP) to manage their Medicare members. To continue compliance into the new year ('2021'), there are multiple data points outlined in the Proposed Solution section of this scope that need to be updated to allow MP to continue processing member transactions properly. | See attached pdf—'MarketProminence Year-end 2021'. | See attached pdf—'MarketProminence Year-end 2021'. | Please verify that all deliverables in the attached file are implemented in test and after internal testing is completed, promoted to production. | The client is responsible for the items listed under client responsibilities in the attached document. Send email to BRM when items are successfully implemented to production. | Any variances determined after loading the January 1st 2021 MMR file will be investigated once the client initiates a new request Deborah Hannon. | MHK/MarketProminence estimates 25 hours to complete this project. 25 hours will be deducted from the prepaid amount. Any hours over the monthly hours will first be deducted from the current years remaining rollover hours. Hours in excess of the monthly and carryover will be billed at the contracted postpaid rate. | Please email a signed copy of this scope to dhannon@mhk.com. Any changes made to this scope will require a new revision and appropriate approvals.
ELD |  | Lance H. (Lance is not shown as a contact in Scope for Elderplan) | 35266 (scope not completed) | 25 |  | Don Tupper (Contact Not found) |  | Elderplan, Inc. (ELD) uses MarketProminence (MP) to manage their Medicare members. To continue compliance into the new year ('2021'), there are multiple data points outlined in the Proposed Solution section of this scope that need to be updated to allow MP to continue processing member transactions properly. | See attached pdf—'MarketProminence Year-end 2021'. | See attached pdf—'MarketProminence Year-end 2021'. | Please verify that all deliverables in the attached file are implemented in test and after internal testing is completed, promoted to production. | The client is responsible for the items listed under client responsibilities in the attached document. Send email to BRM when items are successfully implemented to production. | Any variances determined after loading the January 1st 2021 MMR file will be investigated once the client initiates a new request Lance Horowitz. | MHK/MarketProminence estimates 25 hours to complete this project. 25 hours will be deducted from the prepaid amount. Any hours over the monthly hours will first be deducted from the current years remaining rollover hours. Hours in excess of the monthly and carryover will be billed at the contracted postpaid rate. | Please email a signed copy of this scope to lhorowitz@mhk.com. Any changes made to this scope will require a new revision and appropriate approvals.
EIC |  | Adam K. (no contacts available in Scope in Central) | 35267 (scope not completed) |  |  |  |  | Envision Insurance Company (EIC) uses MarketProminence (MP) to manage their Medicare members. To continue compliance into the new year ('2021'), there are multiple data points outlined in the Proposed Solution section of this scope that need to be updated to allow MP to continue processing member transactions properly. | See attached pdf—'MarketProminence Year-end 2021'. | See attached pdf—'MarketProminence Year-end 2021'. | Please verify that all deliverables in the attached file are implemented in test and after internal testing is completed, promoted to production. | The client is responsible for the items listed under client responsibilities in the attached document. Send email to BRM when items are successfully implemented to production. | Any variances determined after loading the January 1st 2021 MMR file will be investigated once the client initiates a new request Adam Kamen. | MHK/MarketProminence estimates ___ hours to complete this project. ___ hours will be deducted from the prepaid amount. Any hours over the monthly hours will first be deducted from the current years remaining rollover hours. Hours in excess of the monthly and carryover will be billed at the contracted postpaid rate. | Please email a signed copy of this scope to akamen@mhk.com. Any changes made to this scope will require a new revision and appropriate approvals.
EMB |  | Lance H. |  | 35 |  | Christina Tom |  | Emblem Health (EMB) uses MarketProminence (MP) to manage their Medicare members. To continue compliance into the new year ('2021'), there are multiple data points outlined in the Proposed Solution section of this scope that need to be updated to allow MP to continue processing member transactions properly. | See attached pdf—'MarketProminence Year-end 2021'. | See attached pdf—'MarketProminence Year-end 2021'. | Please verify that all deliverables in the attached file are implemented in test and after internal testing is completed, promoted to production. | The client is responsible for the items listed under client responsibilities in the attached document. Send email to BRM when items are successfully implemented to production. | Any variances determined after loading the January 1st 2021 MMR file will be investigated once the client initiates a new request Lance Horowitz. | MHK/MarketProminence estimates 35 hours to complete this project. 35 hours will be deducted from the prepaid amount. Any hours over the monthly hours will first be deducted from the current years remaining rollover hours. Hours in excess of the monthly and carryover will be billed at the contracted postpaid rate. | Please email a signed copy of this scope to lhorowitz@mhk.com. Any changes made to this scope will require a new revision and appropriate approvals.
EON |  | Lance H. |  | 30 |  | Jessica Velez |  | Eon Health Plan, LLC (EON) uses MarketProminence (MP) to manage their Medicare members. To continue compliance into the new year ('2021'), there are multiple data points outlined in the Proposed Solution section of this scope that need to be updated to allow MP to continue processing member transactions properly. | See attached pdf—'MarketProminence Year-end 2021'. | See attached pdf—'MarketProminence Year-end 2021'. | Please verify that all deliverables in the attached file are implemented in test and after internal testing is completed, promoted to production. | The client is responsible for the items listed under client responsibilities in the attached document. Send email to BRM when items are successfully implemented to production. | Any variances determined after loading the January 1st 2021 MMR file will be investigated once the client initiates a new request Lance Horowitz. | MHK/MarketProminence estimates 30 hours to complete this project. 30 hours will be deducted from the prepaid amount. Any hours over the monthly hours will first be deducted from the current years remaining rollover hours. Hours in excess of the monthly and carryover will be billed at the contracted postpaid rate. | Please email a signed copy of this scope to lhorowitz@mhk.com. Any changes made to this scope will require a new revision and appropriate approvals.
GUN |  | Adam K. (Deborah H. was erroneously assigned as BRM) | 35268 | 25 |  | Jessica Griffin (Contact Not found) |  | Quartz (GUN) uses MarketProminence (MP) to manage their Medicare members. To continue compliance into the new year ('2021'), there are multiple data points outlined in the Proposed Solution section of this scope that need to be updated to allow MP to continue processing member transactions properly. | See attached pdf—'MarketProminence Year-end 2021'. | See attached pdf—'MarketProminence Year-end 2021'. | Please verify that all deliverables in the attached file are implemented in test and after internal testing is completed, promoted to production. | The client is responsible for the items listed under client responsibilities in the attached document. Send email to BRM when items are successfully implemented to production. | Any variances determined after loading the January 1st 2021 MMR file will be investigated once the client initiates a new request Adam Kamen. | MHK/MarketProminence estimates 25 hours to complete this project. 25 hours will be deducted from the prepaid amount. Any hours over the monthly hours will first be deducted from the current years remaining rollover hours. Hours in excess of the monthly and carryover will be billed at the contracted postpaid rate. | Please email a signed copy of this scope to akamen@mhk.com. Any changes made to this scope will require a new revision and appropriate approvals.
HFN |  | Lance H. | 35271 | 25 |  | Jim Berlinger (It's probably "James" not "Jim") |  | HF Management Services, LLC. (HFN) uses MarketProminence (MP) to manage their Medicare members. To continue compliance into the new year ('2021'), there are multiple data points outlined in the Proposed Solution section of this scope that need to be updated to allow MP to continue processing member transactions properly. | See attached pdf—'MarketProminence Year-end 2021'. | See attached pdf—'MarketProminence Year-end 2021'. | Please verify that all deliverables in the attached file are implemented in test and after internal testing is completed, promoted to production. | The client is responsible for the items listed under client responsibilities in the attached document. Send email to BRM when items are successfully implemented to production. | Any variances determined after loading the January 1st 2021 MMR file will be investigated once the client initiates a new request Lance Horowitz. | MHK/MarketProminence estimates 25 hours to complete this project. 25 hours will be deducted from the prepaid amount. Any hours over the monthly hours will first be deducted from the current years remaining rollover hours. Hours in excess of the monthly and carryover will be billed at the contracted postpaid rate. | Please email a signed copy of this scope to lhorowitz@mhk.com. Any changes made to this scope will require a new revision and appropriate approvals.
HNE |  | Adam K. | 35272 | 25 |  | Patrick Sullivan |  | Health New England (HNE) uses MarketProminence (MP) to manage their Medicare members. To continue compliance into the new year ('2021'), there are multiple data points outlined in the Proposed Solution section of this scope that need to be updated to allow MP to continue processing member transactions properly. | See attached pdf—'MarketProminence Year-end 2021'. | See attached pdf—'MarketProminence Year-end 2021'. | Please verify that all deliverables in the attached file are implemented in test and after internal testing is completed, promoted to production. | The client is responsible for the items listed under client responsibilities in the attached document. Send email to BRM when items are successfully implemented to production. | Any variances determined after loading the January 1st 2021 MMR file will be investigated once the client initiates a new request Adam Kamen. | MHK/MarketProminence estimates 25 hours to complete this project. 25 hours will be deducted from the prepaid amount. Any hours over the monthly hours will first be deducted from the current years remaining rollover hours. Hours in excess of the monthly and carryover will be billed at the contracted postpaid rate. | Please email a signed copy of this scope to akamen@mhk.com. Any changes made to this scope will require a new revision and appropriate approvals.
HPP |  | Deborah H. | 35273 | 25 |  | Megan Polkus |  | Health Partners Plans (HPP) uses MarketProminence (MP) to manage their Medicare members. To continue compliance into the new year ('2021'), there are multiple data points outlined in the Proposed Solution section of this scope that need to be updated to allow MP to continue processing member transactions properly. | See attached pdf—'MarketProminence Year-end 2021'. | See attached pdf—'MarketProminence Year-end 2021'. | Please verify that all deliverables in the attached file are implemented in test and after internal testing is completed, promoted to production. | The client is responsible for the items listed under client responsibilities in the attached document. Send email to BRM when items are successfully implemented to production. | Any variances determined after loading the January 1st 2021 MMR file will be investigated once the client initiates a new request Deborah Hannon. | MHK/MarketProminence estimates 25 hours to complete this project. 25 hours will be deducted from the prepaid amount. Any hours over the monthly hours will first be deducted from the current years remaining rollover hours. Hours in excess of the monthly and carryover will be billed at the contracted postpaid rate. | Please email a signed copy of this scope to dhannon@mhk.com. Any changes made to this scope will require a new revision and appropriate approvals.
HUM |  | Ian R. | [5 empty] | Humana Inc. (HUM) uses MarketProminence (MP) to manage their Medicare members. To continue compliance into the new year ('2021'), there are multiple data points outlined in the Proposed Solution section of this scope that need to be updated to allow MP to continue processing member transactions properly. | See attached pdf—'MarketProminence Year-end 2021'. | See attached pdf—'MarketProminence Year-end 2021'. | Please verify that all deliverables in the attached file are implemented in test and after internal testing is completed, promoted to production. | The client is responsible for the items listed under client responsibilities in the attached document. Send email to BRM when items are successfully implemented to production. | Any variances determined after loading the January 1st 2021 MMR file will be investigated once the client initiates a new request Ian Robbins. | MHK/MarketProminence estimates ___ hours to complete this project. ___ hours will be deducted from the prepaid amount. Any hours over the monthly hours will first be deducted from the current years remaining rollover hours. Hours in excess of the monthly and carryover will be billed at the contracted postpaid rate. | Please email a signed copy of this scope to irobbins@mhk.com. Any changes made to this scope will require a new revision and appropriate approvals.
KPC |  | Brian M. | [5 empty] | Kaiser Permanente of California (KPC) uses MarketProminence (MP) to manage their Medicare members. To continue compliance into the new year ('2021'), there are multiple data points outlined in the Proposed Solution section of this scope that need to be updated to allow MP to continue processing member transactions properly. | See attached pdf—'MarketProminence Year-end 2021'. | See attached pdf—'MarketProminence Year-end 2021'. | Please verify that all deliverables in the attached file are implemented in test and after internal testing is completed, promoted to production. | The client is responsible for the items listed under client responsibilities in the attached document. Send email to BRM when items are successfully implemented to production. | Any variances determined after loading the January 1st 2021 MMR file will be investigated once the client initiates a new request Brian Mclaughlin. | MHK/MarketProminence estimates ___ hours to complete this project. ___ hours will be deducted from the prepaid amount. Any hours over the monthly hours will first be deducted from the current years remaining rollover hours. Hours in excess of the monthly and carryover will be billed at the contracted postpaid rate. | Please email a signed copy of this scope to bmclaughlin@mhk.com. Any changes made to this scope will require a new revision and appropriate approvals.
KPW(GHC) |  | Brian M | [5 empty] | Kaiser Permanente of Washington (KPW(GHC)) uses MarketProminence (MP) to manage their Medicare members. To continue compliance into the new year ('2021'), there are multiple data points outlined in the Proposed Solution section of this scope that need to be updated to allow MP to continue processing member transactions properly. | See attached pdf—'MarketProminence Year-end 2021'. | See attached pdf—'MarketProminence Year-end 2021'. | Please verify that all deliverables in the attached file are implemented in test and after internal testing is completed, promoted to production. | The client is responsible for the items listed under client responsibilities in the attached document. Send email to BRM when items are successfully implemented to production. | Any variances determined after loading the January 1st 2021 MMR file will be investigated once the client initiates a new request Brian Mclaughlin. | MHK/MarketProminence estimates ___ hours to complete this project. ___ hours will be deducted from the prepaid amount. Any hours over the monthly hours will first be deducted from the current years remaining rollover hours. Hours in excess of the monthly and carryover will be billed at the contracted postpaid rate. | Please email a signed copy of this scope to bmclaughlin@mhk.com. Any changes made to this scope will require a new revision and appropriate approvals.
MHP |  | Adam K. | 35274 |  |  | Tyler Vogt |  | Meridian Health Plan (MHP) uses MarketProminence (MP) to manage their Medicare members. To continue compliance into the new year ('2021'), there are multiple data points outlined in the Proposed Solution section of this scope that need to be updated to allow MP to continue processing member transactions properly. | See attached pdf—'MarketProminence Year-end 2021'. | See attached pdf—'MarketProminence Year-end 2021'. | Please verify that all deliverables in the attached file are implemented in test and after internal testing is completed, promoted to production. | The client is responsible for the items listed under client responsibilities in the attached document. Send email to BRM when items are successfully implemented to production. | Any variances determined after loading the January 1st 2021 MMR file will be investigated once the client initiates a new request Adam Kamen. | MHK/MarketProminence estimates ___ hours to complete this project. ___ hours will be deducted from the prepaid amount. Any hours over the monthly hours will first be deducted from the current years remaining rollover hours. Hours in excess of the monthly and carryover will be billed at the contracted postpaid rate. | Please email a signed copy of this scope to akamen@mhk.com. Any changes made to this scope will require a new revision and appropriate approvals.
MMM |  | Lance H. | 35276 | 50 |  | Jorge Vanga | Sandra Diaz-Rodriguez | MMM Holdings, Inc. (MMM) uses MarketProminence (MP) to manage their Medicare members. To continue compliance into the new year ('2021'), there are multiple data points outlined in the Proposed Solution section of this scope that need to be updated to allow MP to continue processing member transactions properly. | See attached pdf—'MarketProminence Year-end 2021'. | See attached pdf—'MarketProminence Year-end 2021'. | Please verify that all deliverables in the attached file are implemented in test and after internal testing is completed, promoted to production. | The client is responsible for the items listed under client responsibilities in the attached document. Send email to BRM when items are successfully implemented to production. | Any variances determined after loading the January 1st 2021 MMR file will be investigated once the client initiates a new request Lance Horowitz. | MHK/MarketProminence estimates 50 hours to complete this project. 50 hours will be deducted from the prepaid amount. Any hours over the monthly hours will first be deducted from the current years remaining rollover hours. Hours in excess of the monthly and carryover will be billed at the contracted postpaid rate. | Please email a signed copy of this scope to lhorowitz@mhk.com. Any changes made to this scope will require a new revision and appropriate approvals.
MMF |  | Lance H. | 35277 | 50 |  | Jorge Vanga | Vilma Santos-Negron | MMM Holdings, Inc. (MMF) uses MarketProminence (MP) to manage their Medicare members. To continue compliance into the new year ('2021'), there are multiple data points outlined in the Proposed Solution section of this scope that need to be updated to allow MP to continue processing member transactions properly. | See attached pdf—'MarketProminence Year-end 2021'. | See attached pdf—'MarketProminence Year-end 2021'. | Please verify that all deliverables in the attached file are implemented in test and after internal testing is completed, promoted to production. | The client is responsible for the items listed under client responsibilities in the attached document. Send email to BRM when items are successfully implemented to production. | Any variances determined after loading the January 1st 2021 MMR file will be investigated once the client initiates a new request Lance Horowitz. | MHK/MarketProminence estimates 50 hours to complete this project. 50 hours will be deducted from the prepaid amount. Any hours over the monthly hours will first be deducted from the current years remaining rollover hours. Hours in excess of the monthly and carryover will be billed at the contracted postpaid rate. | Please email a signed copy of this scope to lhorowitz@mhk.com. Any changes made to this scope will require a new revision and appropriate approvals.
MVP |  | Lance H. | 35278 | 30 |  | Andrew Hart |  | MVP Health Plan Inc (MVP) uses MarketProminence (MP) to manage their Medicare members. To continue compliance into the new year ('2021'), there are multiple data points outlined in the Proposed Solution section of this scope that need to be updated to allow MP to continue processing member transactions properly. | See attached pdf—'MarketProminence Year-end 2021'. | See attached pdf—'MarketProminence Year-end 2021'. | Please verify that all deliverables in the attached file are implemented in test and after internal testing is completed, promoted to production. | The client is responsible for the items listed under client responsibilities in the attached document. Send email to BRM when items are successfully implemented to production. | Any variances determined after loading the January 1st 2021 MMR file will be investigated once the client initiates a new request Lance Horowitz. | MHK/MarketProminence estimates 30 hours to complete this project. 30 hours will be deducted from the prepaid amount. Any hours over the monthly hours will first be deducted from the current years remaining rollover hours. Hours in excess of the monthly and carryover will be billed at the contracted postpaid rate. | Please email a signed copy of this scope to lhorowitz@mhk.com. Any changes made to this scope will require a new revision and appropriate approvals.
PRS |  | Deborah H. | 35279 | 40 |  | Scarlett Taylor |  | Presbyterian Health Plan (PRS) uses MarketProminence (MP) to manage their Medicare members. To continue compliance into the new year ('2021'), there are multiple data points outlined in the Proposed Solution section of this scope that need to be updated to allow MP to continue processing member transactions properly. | See attached pdf—'MarketProminence Year-end 2021'. | See attached pdf—'MarketProminence Year-end 2021'. | Please verify that all deliverables in the attached file are implemented in test and after internal testing is completed, promoted to production. | The client is responsible for the items listed under client responsibilities in the attached document. Send email to BRM when items are successfully implemented to production. | Any variances determined after loading the January 1st 2021 MMR file will be investigated once the client initiates a new request Deborah Hannon. | MHK/MarketProminence estimates 40 hours to complete this project. 40 hours will be deducted from the prepaid amount. Any hours over the monthly hours will first be deducted from the current years remaining rollover hours. Hours in excess of the monthly and carryover will be billed at the contracted postpaid rate. | Please email a signed copy of this scope to dhannon@mhk.com. Any changes made to this scope will require a new revision and appropriate approvals.
TUF |  | Brian M. |  | 40 |  | Terrance Henderson |  | Tufts Health Plan (TUF) uses MarketProminence (MP) to manage their Medicare members. To continue compliance into the new year ('2021'), there are multiple data points outlined in the Proposed Solution section of this scope that need to be updated to allow MP to continue processing member transactions properly. | See attached pdf—'MarketProminence Year-end 2021'. | See attached pdf—'MarketProminence Year-end 2021'. | Please verify that all deliverables in the attached file are implemented in test and after internal testing is completed, promoted to production. | The client is responsible for the items listed under client responsibilities in the attached document. Send email to BRM when items are successfully implemented to production. | Any variances determined after loading the January 1st 2021 MMR file will be investigated once the client initiates a new request Brian Mclaughlin. | MHK/MarketProminence estimates 40 hours to complete this project. 40 hours will be deducted from the prepaid amount. Any hours over the monthly hours will first be deducted from the current years remaining rollover hours. Hours in excess of the monthly and carryover will be billed at the contracted postpaid rate. | Please email a signed copy of this scope to bmclaughlin@mhk.com. Any changes made to this scope will require a new revision and appropriate approvals.
UMH |  | Adam K. | 35280 | 25 |  | Nadia Zahangir |  | Univ of Maryland Medical Health Plans (UMH) uses MarketProminence (MP) to manage their Medicare members. To continue compliance into the new year ('2021'), there are multiple data points outlined in the Proposed Solution section of this scope that need to be updated to allow MP to continue processing member transactions properly. | See attached pdf—'MarketProminence Year-end 2021'. | See attached pdf—'MarketProminence Year-end 2021'. | Please verify that all deliverables in the attached file are implemented in test and after internal testing is completed, promoted to production. | The client is responsible for the items listed under client responsibilities in the attached document. Send email to BRM when items are successfully implemented to production. | Any variances determined after loading the January 1st 2021 MMR file will be investigated once the client initiates a new request Adam Kamen. | MHK/MarketProminence estimates 25 hours to complete this project. 25 hours will be deducted from the prepaid amount. Any hours over the monthly hours will first be deducted from the current years remaining rollover hours. Hours in excess of the monthly and carryover will be billed at the contracted postpaid rate. | Please email a signed copy of this scope to akamen@mhk.com. Any changes made to this scope will require a new revision and appropriate approvals.